## Tools vs activities TMap
|  | Tools for planning and controlling the test | Testware management tool | Defect management tool | Planning and progress monitoring tool | Workflow tool | Tools for designing the test | Test data tool | Test design tool | Model-based testing tool | Tools for executing the test | Automated test execution tool | Performance, load and stress test tool | Monitoring tool | Code coverage tool | Comparator | Database manipulation tool | Simulator | Stubs and drivers
5.2 Planning phase of the total test process
1 | Establishing the assignment
2 | Understanding the assignment
3 | Analysing the product risks
4 | Determining the test strategy
5 | Estimating the effort |  |  |  | X
6 | Determining the planning |  |  |  | X | X
7 | Defining the test products |  | X
8 | Defining the organisation
9 | Defining the infrastructure
10 | Organising the management |  | X | X | X | X
11 | Determining the test project risks and countermeasures
12 | Feedback and consolidation of the plan
5.3 Control phase of the total test process
1 | Management |  | X | X | X | X
2 | Monitoring |  | X | X | X | X
3 | Reporting |  | X | X | X | X
4 | Adjusting |  |  |  | X | X
6.2 Planning phase
1 | Establishing the assignment
2 | Understanding the assignment
3 | Determining the test basis
4 | Analysing the product risks
5 | Determining the test strategy
6 | Estimating the effort |  |  |  | X
7 | Determining the planning |  |  |  | X | X
8 | Allocating test units and test techniques |  |  |  |  | X
9 | Defining the test products |  | X
10 | Defining the organisation
11 | Defining the infrastructure
12 | Organising the management |  | X | X | X | X
13 | Determining the test project risks and countermeasures
14 | Feedback and consolidation of the plan
6.3 Control phase
1 | Management |  | X | X | X | X
2 | Monitoring |  | X | X | X | X
3 | Reporting |  | X | X | X | X
4 | Adjusting |  |  |  | X | X
6.4 Setting up and maintaining infrastructure phase
1 | Specifying the infrastructure
2 | Realising the infrastructure
3 | Specifying the infrastructure intake |  | X
4 | Intake of the infrastructure |  | X | X
5 | Maintaining the infrastructure
6 | Preserving the infrastructure
6.5 Preparation phase
1 | Collection of the test basis
2 | Creating checklists
3 | Assessing the test basis |  |  | X
4 | Creating the testability review report
6.6 Specification phase
1 | Creation of test specifications |  | X | X |  |  |  | X | X | X |  | X | X
2 | Definition of central starting points |  | X |  |  |  |  | X
3 | Specification of the test object intake |  | X |  |  |  |  | X | X |  |  | X
6.7 Execution Phase
1 | Intake of the test object |  | X | X | [7 empty] | X |  | X |  | X | X | X | X
2 | Preparing the starting points |  | X |  |  |  |  | X |  | X |  | X | X |  |  |  | X
3 | Executing the (re)tests |  | X | X | [5 empty] | X |  | X | X | X | X | X | X | X | X
4 | Checking and assessing test results |  | X | X |  |  |  | X |  |  |  | X | X | X | X | X | X
6.8 Completion phase
1 | Evaluating the test process |  | X | X
2 | Preserving testware |  | X |  |  |  |  | X