## Cover sheet
TMAP Template: Quality Risk Analysis for SAP projects |  |  |  | www.TMAP.net |  |  | © Sogeti 2023
for instructions on how to use this template, please refer to rows 30 and below of this worksheet
Project information
Project Name: | <fill in name>
Responsible Test Lead: | <fill in name>
Document date & version: | <fill in date and version>
Review and approval
Name | Role |  |  | Organisation | Approval date | Version
List of contributors to the SQRA
Name | Role |  |  | Organisation
Risk ranges
| Lower Limit | Upper Limit | counts
Low risk | 0 | 16 | 0
Medium risk | 16 | 40 | 0
High risk | 40 | 75 | 0
Critical | 75 | 100 | 0
How to use this template
This template supports the administration of SAP Quality Risk Analyses
Process steps
1.Fill in the project information and list of participants to the SQRA (rows 6-19 of the template)
2. Complete the list of functional flows in this sheet before holding the SQRA workshop
3. Per functional flow, assign values for Complexity, Impact, Criticality and Frequency (columns D:G)
4. review the upper and lower limits for risk ranges and manually adjust Upper Limits in F25:F27, if necessary
Color coding of cells
Values that are auto-computed have dark amber background & white font |  |  |  |  | like this
values that should be entered or can be adjusted, have light yellow background --> |  |  |  |  | like this
risk classification in column I of the PRA sheet have an intuative color coding - these values and colors will automatically be computed based on PRA input and value limits set for risk categories
Rating guide
Rating | Description
Process Complexity
1 | Very simple process, main flow + max 2 alternate flows visible to the user
2 | Simple process, max 6 alternate flows, max 10 data tables involved
3 | Medium complex algorithm, max 6 alternate flows, max 10 data tables involved
4 | Complex algorithms: Multiple decisions or many dependencies or complex computations
5 | Very complex (combination of complexity factors above)
Technical Impact
1 | Standard SAP, simple parameterizations only
2 | Extensive parameterizations
Or relevant upstream/downstream processing
3 | Simple RICEFW
or data setup that has significant impact on processing (e.g. basic reference model setup)
4 | Normal RICEFW
or processing significant data setup
5 | Complex RICEFW
or high impact (master ) data setup
Business Criticality
1 | Limited impact (may be caught up or corrected without impacting related business processes)
2 | Errors will induce significant hours to be spent on internal corrections or rework
primary business process not affected
3 | Errors are likely to affect primary business processes (e.g. standstill or under performance) but impact will be local and have no external visibility
or are likely to have internal financial impact, but financial impact limited to single transactions
4 | Errors may lead to significant financial losses (normally on local scale)
or may have external visibility
5 | Errors may have structural negative impact on profitability or company image
Frequency of use
1 | Used incidentally / on a monthly basis or less
2 | Used on Weekly basis
Or monthly basis and over 10% of all users involved
3 | Normal use is on a daily basis
4 | Used continually (during office hours or normal productive hours)
5 | Heavy duty: continual usage by a significant number of users
This document is derived from the CRESCENT template for Product Risk Analysis

## SQRA sheet
SAP Quality Risk Analysis for <fill in name> |  | IT |  | Business |  |  | Risk | © Sogeti 2023 www.TMAP.net
Process group | Business process | Com-plexity | Tech-nical Impact | Busi-ness Criti-cality | Fre-quency of use | Score | Risk Class | Comment
….
…
| …. |  |  |  |  | 0 | _
| …. |  |  |  |  | 0 | _
| …. |  |  |  |  | 0 | _
…
| …. |  |  |  |  | 0 | _
| …. |  |  |  |  | 0 | _
| …. |  |  |  |  | 0 | _

## SQRA Example
SAP Quality Risk Analysis - Example |  | IT |  | Business |  |  | Risk | © Sogeti 2023 www.TMAP.net
Process group | business process | Com-plexity | Tech-nical Impact | Busi-ness Criti-cality | Fre-quency of use | Score | Risk Class | Comment
1 Organizational Structure and Master Data
1.1 Organizational Structure and Master Data
| 1.1.1 Organizational Structure | 4 | 4 | 2 | 3 | 40 | B
| 1.1.2 Warehouse Structure | 1 | 1 | 1 | 1 | 4 | D
| 1.1.3 Stock types | 1 | 1 | 1 | 1 | 4 | D
| 1.1.4 Product Master | 2 | 2 | 5 | 2 | 28 | C
| 1.1.5 Allergens | 3 | 3 | 3 | 1 | 24 | C
| 1.1.6 Batch Management | 3 | 3 | 3 | 1 | 24 | C
| 1.1.7 HU Numbering | 1 | 1 | 3 | 1 | 8 | D
| 1.1.8 Pallet Labelling | 4 | 5 | 4 | 5 | 81 | A
| 1.1.9 Resource management | 1 | 1 | 3 | 1 | 8 | D
| 1.1.10 Packaging Specification | 1 | 1 | 3 | 1 | 8 | D
| 1.1.11 Hazardous Substance Master | 1 | 1 | 3 | 1 | 8 | D
| 1.1.12 Quality Inspection Rule | 1 | 1 | 3 | 1 | 8 | D
2 Inbound Processes
2.1 Inbound from External Vendor
| 2.1.1. Inbound from External Vendor - Pallet Receiving | 4 | 4 | 5 | 5 | 80 | A
| 2.1.2 Inbound from External Vendor - Bulk Receiving | [6 empty] | Out of scope
2.2 Stock Transfer from DC to DC
| 2.2.1 Stock Transfer from another DC with TM | 3 | 4 | 5 | 3 | 56 | B
| 2.2.2 Stock Transfer from another DC without TM | 3 | 4 | 5 | 3 | 56 | B
| 2.2.3 Stock Transfer from another EWM managed DC | 2 | 4 | 5 | 3 | 48 | B
2.3 Store to Store with Cross Docking
| 2.7.1 Store to Store Process | 4 | 5 | 5 | 4 | 81 | A
| 2.7.2 Seasonal returns Process | 2 | 2 | 3 | 3 | 24 | C
| 2.7.3 Extra Push | 2 | 2 | 3 | 3 | 24 | C
| 2.7.4. Cross-docking between Warehouses | 2 | 2 | 3 | 3 | 24 | C
| 2.7.5. Crossdocking Seasonal between warehouses | 2 | 2 | 3 | 3 | 24 | C
3 Outbound Processes
3.1 Standard Customer Deliveries (for Sales Orders)
| 3.1.1 Standard Outbound - Core Process steps | 2 | 2 | 2 | 2 | 16 | C
| 3.1.2 Layer picking from the Pick-face area | 2 | 2 | 2 | 2 | 16 | C
| 3.1.4 Pick-face - Less than pallet (Piece picking) | 2 | 2 | 2 | 2 | 16 | C
| 3.1.5 Short shelf-life | 2 | 2 | 2 | 2 | 16 | C
| 3.1.6 Pallet Reconfiguration (Subcontracting) | 2 | 2 | 2 | 2 | 16 | C
3.2 Stock Transfer DC to DC
| 3.2.1 Outbound to DC - Full Pallet | 3 | 3 | 3 | 3 | 36 | C
| 3.2.2 Outbound to DC - Partial pallet Inter DC process (Regular products) | 3 | 3 | 3 | 3 | 36 | C

## Validation lists (hidden)
validation lists
These validation lists are used for the picklists on RPA sheet - editing this sheet is not recommended
rating scores | priority categories
1 | Low
2 | Medium
3 | High
4 | Critical
5 | _